## Activities
Activity | Hours/Week | Days/Month | Days/Year | Number of persons | Man-days/Year | Field of Activity
Flyer production |  | 4 |  | 1 | 48 | Communication
Electrical tests |  |  | 2 | 1 | 2 | Facility-Management
Stakeholder Meeting |  |  | 4 | 2 | 8 | Networking
Social Media Entrys | 2 |  |  | 1 | 13 | Communication
Public Tours |  |  | 5 | 1 | 5 | Communication
Art Class Teaching | 4 |  |  | 1 | 26 | Facility-Management
Cleaning Workshop Room | 2 |  |  | 1 | 13 | Educational Work
Preparing Workshop Room | 1 |  |  | 1 | 6.5 | Organizational Support
Volunteer Meeting |  |  | 4 | 1 | 4 | Networking
Poster production |  | 2 |  | 1 | 24 | Communication
INSTRUCTIONS 1. Select the Fields of Activities-Tab - Create the Fields of Activities-Tab. Those Entries cluster all your activities. The goal is here to get an impression which competencies are needed to run your project and what staff requirements your project needs. When you realize later on that you need further fields of activites - just add them in this tab or replace the placeholder-entrys. 2. Select the Activities-Tab - write down activities that you found out about in the "Activiites-Processes" Blueprint. Estimate how much time those activities consume. You can write your estimation in either column - Hours/Week, Days/Month, Days/year. Only use one column at a time. EXAMPLE: We will have 4 stakeholder meetings per year and it takes us two persons to run this activity. Another EXAMPLE: We will need one hour per week to prepare the workshop room - this is done by one person. 3. Overview - Go to the "Fields of Activities"-Tab and have a look at the pie chart to see what fields of activities take how much resources. This will help you to guess what and how much personnel you will need for your project.

## Field of Activities
Fileds of Activities | Days/Year
Communication | 90
Facility-Management | 28
Cooking | 0
Accounting | 0
Organizational Support | 6.5
Transport | 0
Networking | 12
Educational Work | 13
Sample 1 | 0
Sample 2 | 0
Sample 3 | 0
Sample 4 | 0
Sample 5 | 0
Sample 6 | 0
Sample 7 | 0
Sum Man-Days per year | 136.5